## Activity Log
# | Phase | Activity | Bucket | Tool / Method | LLM? | Est. Tokens | Est. Cost (USD) | Time (min) | Time Basis | Notes
1 | Explore | Locate the project; read Similar Pictures end to end; write the Similar Videos strategy and four decisions for the owner | A - LLM tokens | Read/Write | Yes | 15000 | 0.6 | 6 | estimate | owner: use the recommended defaults
2 | Gate | Baseline quality gate before any change | B - Local ($0) | build.ps1 -All | No |  | 0 | 1.7 | measured | PASS, 584 unit + 27 QA
3 | Refactor | ENH-12 kit: move ByteSize/PauseToken/FileBytes/GrayImage/ImageHasher, generic ReviewFolder; UseKit opt-in; golden rule 1 + architecture docs | A - LLM tokens | Write/Edit | Yes | 18000 | 0.7 | 10 | estimate | 3 copies + 4 duplicate test files removed
4 | Gate | Pre-commit gate on the kit commit | B - Local ($0) | build.ps1 -NoPrompt | No |  | 0 | 0.5 | measured
5 | Refactor | Kit part 2: FileRecordCache, IncrementalScanner, FileNames, Ranking, SampleScene; Similar Pictures delegates (API unchanged) | A - LLM tokens | Write/Edit | Yes | 16000 | 0.6 | 9 | estimate | picture tests unchanged and green
6 | Bugfix | CA1000 static-on-generic, ScanProgress name clash, three shell-escaping slips on a backslash literal | A - LLM tokens | Edit | Yes | 6000 | 0.22 | 4 | estimate | waste - see journal pitfall
7 | Build | Hand-written Media Foundation interop: Source Reader, Sample, Buffer, Attributes, Sink Writer (no NuGet) | A - LLM tokens | Write | Yes | 14000 | 0.55 | 8 | estimate | worked first time
8 | Build | Engine: VideoDecoder/ReaderSession (exact seek, stride, rotation), record + cache, scanner (Live Photos), matcher, keeper ranking, mover, settings, report, sample set | A - LLM tokens | Write | Yes | 34000 | 1.3 | 18 | estimate
9 | Tests | TestVideoWriter (encode MP4s at test time) + Media Foundation round-trip tests | A - LLM tokens | Write | Yes | 9000 | 0.35 | 5 | estimate | no binary test files
10 | Calibrate | Probe: per-frame distances across re-encodes; found codec padding (160x88 decoded as 160x96) and brittle per-frame dHash | A - LLM tokens | Write/Edit | Yes | 14000 | 0.5 | 9 | estimate | -> crop to aperture; judge dHash on the mean
11 | Calibrate | Run the probes | B - Local ($0) | dotnet test | No |  | 0 | 1 | measured
12 | Build | Review UI: VideoCardControl (film strip) + SimilarVideosControl | A - LLM tokens | Write | Yes | 22000 | 0.85 | 10 | estimate
13 | Tests | 8 unit-test files + the scan -> group -> move -> rescan -> undo pipeline test + kit helper tests | A - LLM tokens | Write | Yes | 30000 | 1.15 | 15 | estimate | all 622 green on the first run
14 | Tests | Unit + QA runs | B - Local ($0) | dotnet test | No |  | 0 | 1 | measured | 622 unit + 30 QA
15 | Tests | QA test (real plugin, sample, click) + DocShots hook; card layout fix after looking at the screenshot | A - LLM tokens | Write/Edit | Yes | 8000 | 0.3 | 5 | estimate
16 | Docgen | Regenerate DocShots screenshots (twice) | B - Local ($0) | dotnet run | No |  | 0 | 0.8 | measured
17 | Docs | FEATURE.md, requirement doc (SVD-1..20), user guide, manual section, hubs, README row, Pages card, kit README | A - LLM tokens | Write | Yes | 24000 | 0.9 | 12 | estimate
18 | Docgen | 20 requirement + 11 traceability rows, SVD id in check_docs regex | A - LLM tokens | Write | Yes | 9000 | 0.35 | 4 | estimate
19 | Docgen | Regenerate requirements/traceability xlsx + HTML user manual; docs check | B - Local ($0) | python + powershell | No |  | 0 | 0.4 | measured | cleanliness check PASSED
20 | Gate | Full quality gate | B - Local ($0) | build.ps1 -All | No |  | 0 | 1.7 | measured | PASS, 652 tests, 93.9%
21 | Release | CHANGELOG 2.6.0, journal phase 25, DevEconomics, PM trackers, memory note | A - LLM tokens | Write/Edit | Yes | 12000 | 0.45 | 8 | estimate | this release entry
22 | Gate | Storage report | B - Local ($0) | node storage-report.mjs | No |  | 0 | 0.2 | measured | docs/pm/STORAGE.md
TOTAL (direct, sum of activities)
Note on A1: AUTO-GENERATED by tools/docgen/build_deveconomics.py - do NOT edit this workbook by hand. Edit the script's data tables and run: python tools/docgen/build_deveconomics.py

## Feature Summary
Feature | Date | Model | Activities | LLM (A) | Local/Remote (B/C) | Prod. KLOC | Est. tokens (direct) | Direct LLM cost EST ($) | Context/cache overhead EST ($) | Total cost EST ($) | Total cost ACTUAL ($) | Cost variance ($) | Local time (min) | Total time EST (min) | Total time ACTUAL (min) | $/KLOC EST | Notes
Prior releases (host + 10 features + quality/docs/CI/release infra, through v2.5.0) | 2026-06-19..10-30 | Opus (multi-session) |  |  |  | 12.33 | 3161764 |  |  | 126.7 |  |  |  | 1162 |  | 10.28 | Phases 1-17 predate DevEconomics tracking (rough estimate); includes the tracked v2.1.0-v2.5.0 releases.
Similar Videos (+ shared helper kit) | 2026-10-31 | Opus 5.5 | 22 | 14 | 8 | 2.6 | 231000 | 8.82 | 22 | 30.82 |  |  | 7.3 | 130.3 |  | 11.85 | Estimate; reconcile ACTUAL via /cost. Phase 3 of the Storage Studio plan, own plugin, plus the ENH-12 helper kit; single session.
APP TOTAL (est) | [16 empty] | Whole-app development to date (foundation + tracked features).
Note on A1: AUTO-GENERATED by tools/docgen/build_deveconomics.py - do NOT edit this workbook by hand. Edit the script's data tables and run: python tools/docgen/build_deveconomics.py

## Trend
DevEconomics trend - estimate vs actual per feature
AUTO-GENERATED by tools/docgen/build_deveconomics.py - do NOT edit this workbook by hand. Edit the script's data tables and run: python tools/docgen/build_deveconomics.py
As features accumulate, each row in 'Feature Summary' adds a point here. The chart compares estimated vs actual cost so the estimate error trends toward zero. Fill the ACTUAL columns from /cost after each feature, then re-run the generator.

## ReadMe
DigitalSecretary - DevEconomics workbook
AUTO-GENERATED by tools/docgen/build_deveconomics.py - do NOT edit this workbook by hand. Edit the script's data tables and run: python tools/docgen/build_deveconomics.py
Purpose | Per-activity cost + time ledger for codeless development, with per-feature estimate-vs-actual tracking and a trend chart.
Cost buckets | A = LLM tokens (the only metered cost); B = local compute ($0 tokens); C = remote/network ($0 tokens).
Rate card (Opus 4.8, $/1M tok) | input 5.0, output 25.0, cache-read 0.5, cache-write 6.25.
Truth & estimates | Token/cost for LLM rows are ESTIMATES (the model can't read its own meter). Local times are MEASURED from command output where captured. Per-feature ACTUAL cost comes from /cost (Claude Code) or the Anthropic Console - fill columns L/P in Feature Summary, then re-run.
This release | 22 activities (14 LLM / 8 local¦remote); ~$30.82 est; ~130.3 min est (~7.3 min measured local compute).
Whole app to date (est) | ~14.93 prod KLOC; ~$157.52 est; ~21.5 h est. Foundation portion is a ROUGH pre-tracking estimate.
Regenerate | python tools/docgen/build_deveconomics.py
Companion | docs/DEVECONOMICS.md (narrative + improvement levers); docs/DEVELOPMENT_JOURNAL.md (what/why).